# NPRB 2301: Tasks, Roles and Manuscript Plans

# Project Management

TASK: Biannual reports (Jan/July) - Cindy

TASK: Budget management/invoicing - Each person with a budget manages their own

TASK: Manage Research Workspace/Information Flow

TASK: Data management - Cindy

TASK: Data library in RW - Cindy

TASK: Final report - Cindy/All

# Preparation

- Sample Inventory

  - TASK: Maintain up to date inventory of samples (Cindy/Darcie)

  - TASK: Selection of samples (All)

  - TASK: Maintain tracking of all samples that are in process (Cindy with input from All)

- Sample Prep

  - TASK: Separation of layers (Cindy/Darcie)

- Sample pre-processing

  - TASK: Spinning a small number of samples (Cindy/Darcie after input from Bruce)

  - TASK: Drying (Cindy/Darcie)

- Sub-sample for isotopes and AMS

  - TASK: Ship dried samples to Taylor (Cindy)

  - TASK: Sub-sample for isotopes (Taylor)

  - TASK: Ship AMS samples to WHOI (Taylor)

# Objective 1

- Evaluate 14C values in PSS and SD eye lens cores (earliest material) and outer layers (recent material) as an indicator of age.

  - TASK: AMS (Taylor)

  - TASK: Chronology explorations (Allen/Bruce)

- Assess the eye lens 14C chronology by comparison with validated ages of SD.

  - TASK: Age spiny dogfish and calculate birth year (Cindy/Beth) - Cindy needs to review data of eye collections, prioritize spine ageing

  - TASK: compare spine birth year to 14C birth year

- Estimate plausible ranges of age-at-length, age-at-maturity, and lifespan of PSS.

  - TASK: run growth models with sensitivities (Allen/Beth?)

Potential Manuscripts

- Dogfish chronology (Allen)

- PSS growth model with diameters (Allen/Beth)

- Potentially combined with below: PSS 14C age and life history

  - Protein turnover (Dan/Bruce)

  - Ties to maturity (Beth/Cindy)

  - CSIAA/stable isotopes (Taylor)

# Objective 2

- Investigate sources of potential variation in isotopic values (13C, 14C, and 15N) of shark eye lens protein.

  - TASK:

- These include

  - sample quality (e.g., freezing/thawing altering the structure of the eye lens),

    - TASK: notes on transport issues, how samples delaminate, qualitative discussion of potential impacts (Cindy/All)

  - protein turnover in eye lenses,

    - TASK: Soluble:insoluble ratio evaluation (Bruce/Dan)

  - dietary and maternal contributions

    - TASK: Run bulk isotopes (Taylor)

    - TASK: Analysis TBD (Taylor)

  - Habitat, depth, and region.

    - TASK: Same as above

  - Ontogenetic diet changes

    - TASK: Run CSIAA samples (Taylor)

Potential Manuscripts:

- 1-2 manuscripts

- 14C data published first for context (or at least analyzed), need age relevance

- Isotope ecology of PSS (Taylor plus others that want to bring in): all isotopes together

- Could reframe and combine obj 1 and obj 2

# Objective 3

- Estimate age-related life history parameters (and associated uncertainty) used in stock assessments and test more robust stock assessment approaches.

  - TASK: Natural mortality analysis (in conjunction with other AK elasmos) - Cindy

  - TASK: Run through DLMs with simulated values where needed (i.e., ORCS) - Cindy

Potential Manuscripts

- Reevaluation of elasmobranch natural mortality estimates and their use in stock assessment in Alaska (Tribuzio, Matta, others?)

- Refining the refined ORCS specific to AK stock assessment of severely data-limited PSS (Tribuzio, Cope, Free, Matta, others?)

- PSS demographic modeling (part of G. Dunne’s PhD, but informed by our results)

- DLM simulations/evaluation (may overlap with G. Dunne’s work and potentially combined with above manuscript, details TBD)